## Function Defect Log
Project Name |  | EGPAF Integrated Health Data Management System (EIHDMS) UPGRADE |  |  | Project REF |  | #001-C-2018 (Support & Maintenance Phase Oct2018 - OCT2019)
Defect ID | Function | Description | Reported By | Date Reported |  | Severity |  | Priority | Status | Remarks | Date Resolved
DF1 |  | Provide for editing of phone contact details incase a phone number is tagged to a wrong facility or changes facilities | Albert | 28-08-18 |  | H |  | H | In Progress | Add window to edit base_data and re-pivot surge data
DF2 |  | Slow speed of data retrieval when viewing reports | Albert | 28-08-18 |  | H |  | M | In Progress | To create base data tables per report form group as opposed to the current base data per report form
DF3 |  | Provision for editing of received SMS by Admin incase of wrong format or passed deadline | albert | 28-08-18 |  | M |  | M | Completed | Added Edit SMS item under Data Menu that is only accessible by users that are Gen Admins
DF4 |  | Capture updated Ariel report form data elements as well as it's entry screen in the database | Emma | 31-08-18 |  | M |  | M | Completed | Completed and updated in the production database
DF5 |  | Unable to capture data for report form LQAS | Albert | 30-08-18 |  | M |  | H | Completed | LQAS is added as a Report for Data Entry capture only. 1.Either we do achange in the data dictionary and group the data elements or we use the current entry screen to enter the data
DF6 |  | Send feedback message when an SMS is sent | Albert | 02-08-18 |  | M |  | M | In Progress
DF7 |  | Capture data dictionaries for Hibrid forms and update the database | Emma | 02-08-18 |  | M |  | M | In Progress
DF8 |  | Provide for provsion for viewing and editing existing data | Albert | 02-08-18 |  | M |  | M | In Progress
DF9 |  | Remove page breaks from downloaded excel templates | Albert | 02-08-18 |  | M |  | M | Pending
DF10 |  | Capture data dictionary for Pediatric TB intensified Cases and update database. Create a customized entry screen for patient level entry | Emma | 28-08-18 |  | M |  | M | In Progress
DF11 |  | Cater for changing phone contacts | Albert | 28-08-18 |  | H |  | M | In Progress | Add entity_id and entity_type to interface_data_sms table and change the sms received dahboard to lookup for thr entity name using the entity in the interface_data_sms table
DF12 |  | The homepage is not being utilsed. A default dashboard should be added | Eliab | 21-09-18 |  | M |  | M | In Progress | The EGPAF surge dashboard will be displayed on the homepage by default
DF13 |  | Need to add reporting Period Filters on the dynamic report(i.e. Jan 1, Dec 12, Quarter 1…etc.) | Eliab | 21-09-18 |  | M |  | M | In Progress
DF14 |  | A discliamer should be added on the dashboards indicating that the data is for recent periods only | Eliab | 21-09-18 |  | M |  | M | In Progress
DF15 |  | Make the Resources Menu accessible over the public IP address. | Eliab | 21-09-18 |  | M |  | M | Pending | To Contact the IT team at EGPAF(Godwin) to ensure the public ip is also accessible internally
DF15 |  | Add the EGPAF PowerBI link as a menu item on the database | Eliab | 21-09-18 |  | M |  | M | In Progress
DF16 |  | The need to capture phone contact user Name for easy identification. | Albert | 20-09-18 |  | M |  | M | In Progress | Phone User Name fiels to be added to the phone_contact form
DF17 |  | Chenge the EPI Data form to cater for Outreach Sites per facility | Albert | 20-09-18 |  | H |  | H | In Progress | The customised entry screen has been completed. Vincent says the form has been changed and he will give an update on Monday abot what has been changed
DF18 |  | Add a Column for district on the SMS received dashboard | Albert | 20-09-19 |  | M |  | M | In Progress

## Lookup
Pending
In Progress
Completed