## Function Defect Log
Project Name |  | EGPAF Integrated Health Data Management System (EIHDMS) UPGRADE |  |  | Project REF |  | #001-C-2018 (Support & Maintenance Phase Oct2018 - OCT2019)
Defect ID | Function | Description | Reported By | Date Reported |  | Severity |  | Priority | Status | Remarks | Date Resolved
DF1 |  | Provide for editing of phone contact details incase a phone number is tagged to a wrong facility or changes facilities | Albert | 28-08-18 |  | H |  | H | In Progress | Add window to edit base_data and re-pivot surge data
DF2 |  | Slow speed of data retrieval when viewing reports | Albert | 28-08-18 |  | H |  | M | In Progress
DF3 |  | Provision for editing of received SMS by Admin incase of wrong format or passed deadline | albert | 28-08-18 |  | M |  | M | Completed | Added Edit SMS item under Data Menu that is only accessible by users that are Gen Admins
DF4 |  | Capture updated Ariel report form data elements as well as it's entry screen in the database | Emma | 31-08-18 |  | M |  | M | Completed
DF5 |  | Unable to capture data for report form LQAS | Albert | 30-08-18 |  | M |  | H | Completed | LQAS is added as a Report for Data Entry capture only. 1.Either we do achange in the data dictionary and group the data elements or we use the current entry screen to enter the data
DF6 |  | Send feedback message when an SMS is sent | Albert | 02-08-18 |  | M |  | M | In Progress
DF7 |  | Capture data dictionaries for Hibrid forms and update the database | Emma | 02-08-18 |  | M |  | M | In Progress
DF8 |  | Provide for provsion for viewing and editing existing data | Albert | 02-08-18 |  | M |  | M | In Progress
DF9 |  | Remove page breaks from downloaded excel templates | Albert | 02-08-18 |  | M |  | M | Pending
DF10 |  | Capture data dictionary for Pediatric TB intensified Cases and update database. Create a customized entry screen for patient level entry | Emma | 28-08-18 |  | M |  | M | In Progress
DF11 |  | Cater for changing phone contacts | Albert | 28-08-18 |  | H |  | M | In Progress
DF12 |  | The homepage is not being utilsed. A default dashboard should be added | Eliab | 21-09-18 |  | M |  | M | In Progress
DF13 |  | Need to add reporting Period Filters on the dynamic report(i.e. Jan 1, Dec 12, Quarter 1…etc.) | Eliab | 21-09-18 |  | M |  | M | In Progress
DF14 |  | A disclimer should be added on the dashboards indicating that the data is for recent periods only | Eliab | 21-09-18 |  | M |  | M | In Progress
DF15 |  | The need to capture phone contact user Name for easy identification | Albert | 20-09-18 |  | M |  | M | In Progress
DF16

## Lookup
Pending
In Progress
Completed